CAPSTONE PROJECT REPORT

Report 2 – Project Management Plan

– Hanoi, Oct 2026 –

Table of Contents

Change Log	3

I. Project Overview	4

1. Scope and Purpose	4

2. Assumptions & Constraints	5

3. Cost & Time Estimations	6

4. Capacity Planning	9

5. Project Objectives	9

6. Risks and Mitigations	10

II. Management Approach	11

1. Project Process/Methodology	11

2. Quality Management	12

3. Project Training Plan	14

4. Responsibility Assignments	15

5. Project Communications	18

6. Configuration Management	18

6.1 Document Management	18

6.2 Source Code Management	19

6.3 Tools & Infrastructures	20

# Change Log

| Date | A* M, D | In charge | Change Description |
| --- | --- | --- | --- |
| 19/09/2026 | A | PTDuong | Create initial report |
| 05/10/2026 | M | PTDuong | Re-baseline scope, WBS, quality plan and RACI against Report 3 |
| 08/10/2026 | M | PTDuong | Clarify MVP/Jira boundary and SRS roles/Project authority; add Kanban diagram and gates; rebalance Cycle 2 foundation, align WBS/RACI/tests and define Version 1–3 dependencies/demos. |

*A - Added M - Modified D - Deleted

# I. Project Overview

## 1. Scope and Purpose

T-Solve (Ticket Solution Repository Application) is a web application that stores and reuses resolution knowledge from handled Jira issues. Each Ticket is a snapshot with one Solution and optional Evidence. The project will deliver a 14-week MVP and its management, requirements, design, test and user documentation. Jira continues to manage issue status, assignment, SLA and escalation; T-Solve reads Jira and does not change its issue lifecycle.

The MVP serves one Workspace containing Departments and Projects. Each Project belongs to one Department and links to exactly one Jira project. Ticket visibility follows Department access; writing Solutions requires Project membership; review and import are limited to Projects managed by the product Project Manager. Staff Departments are derived from Project memberships, while Project Manager Departments are assigned by Admin.

Account roles are Admin, Project Manager and Staff, fixed when each account is added. Guest is an actor who has not signed in, not an account role. Admin manages accounts, Workspace information, Departments and the assignment of Project Managers to Departments.

A Project Manager adds Projects only within assigned Departments and becomes the Project Manager and a member of each Project added. That Project Manager configures or removes the Projects they manage and manages Active Staff membership, field mapping, Done statuses and review ranges. Admin has no general Project-management authority. The exception is handing each Active Project to another Active Project Manager assigned to the same Department before deactivating its current Project Manager; deactivation is blocked if a replacement is unavailable.

The capstone PM coordinates the student team, schedule and academic deliverables; the product Project Manager is an application role. No relationship or dependency on another capstone project is identified in the project introduction or SRS. Jira is an external system integration, not a relationship with another capstone project.

The nine functional groups below define the MVP. The exclusions bound the deliverables and prevent expansion of the agreed scope.

| No | Feature | Functions |
| --- | --- | --- |
| 1 | Role-Based Access Control | Google OIDC; fixed Admin, Project Manager and Staff roles; Guest sign-in actor; account/session controls; Department visibility, Project membership and Jira linking. |
| 2 | Workspace & Department Management | One Workspace; Admin maintains company/Jira site settings and Departments, assigns Project Managers to Departments, and deletes/restores Departments. |
| 3 | Jira Integration | Project Manager adds/configures/removes Projects in assigned Departments, becomes manager of Projects added, and manages Staff membership/settings; read-only per-Project tokens; external Jira App/APIs. |
| 4 | Solution Authoring & Standardisation | Solution Form; optional Ollama drafting/rewriting; Evidence; Draft; changes resubmission. |
| 5 | Review & Approval Workflow | Project Review Queue; approve/reject/request changes; batch approve/reject; Expired recovery; unpublish/re-publish; history and emails. |
| 6 | Ticket Import & Repository | On-demand Jira/CSV/manual import; import Drafts; unique Ticket IDs; direct publication; ticket details/history. |
| 7 | Intelligent Retrieval | Published-ticket keyword/semantic Search, filters and Jira suggestions; keyword fallback. |
| 8 | Reuse & Feedback | Helpful/not helpful and optional comments through web/Jira; reuse/Feedback reporting. |
| 9 | Dashboard & Audit | Department/Workspace dashboards and Admin-only audit viewing. |
| — | Out of Scope | Jira issue/lifecycle management; multiple Workspaces; other identity providers/trackers; non-Jira Projects; category/tag; grouped review; scheduled Jira pulling; direct Published Solution editing; in-app notifications; phone/tablet support. |

## 2. Assumptions & Constraints

| No | Description | Note |
| --- | --- | --- |
| Assumptions |  |  |  |
| 1 | Pilot Jira administrator supplies read-only Browse projects tokens and installs the Jira App; Google OIDC and SMTP access are available. | External interfaces |
| 2 | Representative sample/anonymized data are available for one Workspace and multiple Departments/Projects. | Test data |
| 3 | Lecturer and pilot users are available for milestone review and acceptance testing. | Project management |
| 4 | All five members provide 36 hours/week and contribute to technical work alongside their assigned PM/BA/Developer/Tester responsibilities. | Resources |
| 5 | Jira remains the source for issue lifecycle; Project Managers perform product review within their assigned Projects. | Scope |
| Constraints |  |  |  |
| 1 | Complete the 14-week project by 11/12/2026; total effort 252 md at 8 hours/md. | Schedule |
| 2 | Review all documents/code before delivery. Import confirmation is Project Manager approval; Published Solutions are immutable and have no versions. | Quality |
| 3 | One fixed role/user; Department visibility, Project-based author/review permissions; Google OIDC only, no stored passwords. | Security |
| 4 | Ticket states: Pending review, Changes requested, Published, Rejected, Unpublished, Expired. Draft is separate; transitions follow the defined Ticket lifecycle. | Quality |
| 5 | Meet current SRS performance/interface rules: Search and Issue Panel within 2 seconds for ≤50,000 tickets; desktop browser support only. | Quality |
| 6 | Before Ollama/OpenRouter calls mask email, phone, recognized names, secrets and IP; never send Evidence. Protect tokens/Evidence; use HTTPS; daily backups retained 14 days. | Security |
| 7 | CI build/tests and SonarQube pass before merge; 0 Critical issues. Jira import is user-triggered, read-only and ≤100 resolved issues/requests. | Quality / interfaces |

## 3. Cost & Time Estimations

| # | Work Package | Effort (md)* | Due Date |
| --- | --- | --- | --- |
| 1 | Stage 1: Project Initiating (week 1) | 18 | W1 (11/09/2026) |
| 1.1 | Report 1 (Project Introduction) | 18 | W1 (11/09/2026) |
| 2 | Stage 2: Project Planning & Initial Requirements (weeks 2–3) | 36 | W3 (25/09/2026) |
| 2.1 | Report 3: SRS v0.9 (Overall Requirement) | 9 | W2 (18/09/2026) |
| 2.2 | Vertical Prototypes (Code Demo) | 21 | W3 (25/09/2026) |
| 2.3 | Report 2: Project Management Plan initial baseline | 6 | W3 (25/09/2026) |
| 3 | Stage 3: Software Design (weeks 4–5) | 36 | W5 (09/10/2026) |
| 3.1 | Vertical Prototypes (Proof Of Concepts) | 10 | W4 (02/10/2026) |
| 3.2 | Report 4: SDS v1.0 (High Level Design Specifications) | 8 | W4 (02/10/2026) |
| 3.3 | Report 5: Test Planning | 9 | W5 (09/10/2026) |
| 3.4 | Report 3: detailed-requirements baseline review | 4 | W5 (09/10/2026) |
| 3.5 | Figma design (overall UI/UX wireframes) | 5 | W5 (09/10/2026) |
| 4 | Stage 4: Implementation (weeks 6–11) | 108 | W11 (20/11/2026) |
| 4.1 | Implementation Cycle 1 (weeks 6–7) | 36 | W7 (23/10/2026) |
| 4.1.1 | Report 4: Detailed Design Specifications (SDS) v1.1 | 2 | W6 (16/10/2026) |
| 4.1.2 | Figma design – Cycle 1 | 2 | W6 (16/10/2026) |
| 4.1.3 | Role-Based Access Control | 6 | W7 (23/10/2026) |
| 4.1.4 | Workspace & Department Management | 5 | W7 (23/10/2026) |
| 4.1.5 | Jira Integration and Shared Data/API Foundation | 9 | W7 (23/10/2026) |
| 4.1.6 | Code Package & Unit Testing Report – Cycle 1 | 4 | W7 (23/10/2026) |
| 4.1.7 | Report 5: Integration Test Cases – Cycle 1 | 1 | W7 (23/10/2026) |
| 4.1.8 | Report 5: Integration Test Report – Cycle 1 | 2 | W7 (23/10/2026) |
| 4.1.9 | Report 3: SRS change-impact review – Cycle 1 | 1 | W7 (23/10/2026) |
| 4.1.10 | Software Package Version 1 | 1 | W7 (23/10/2026) |
| 4.1.11 | Defect correction and regression – Cycle 1 | 3 | W7 (23/10/2026) |
| 4.2 | Implementation Cycle 2 (weeks 8–9) | 36 | W9 (06/11/2026) |
| 4.2.1 | Report 4: Detailed Design Specifications (SDS) v1.2 | 2 | W8 (30/10/2026) |
| 4.2.2 | Figma design – Cycle 2 | 2 | W8 (30/10/2026) |
| 4.2.11 | Ticket/Solution/Evidence Foundation & Ticket Detail | 4 | W9 (06/11/2026) |
| 4.2.3 | Solution Authoring & Standardisation | 8 | W9 (06/11/2026) |
| 4.2.4 | Review & Approval Workflow | 8 | W9 (06/11/2026) |
| 4.2.5 | Code Package & Unit Testing Report – Cycle 2 | 4 | W9 (06/11/2026) |
| 4.2.6 | Report 5: Integration Test Cases – Cycle 2 | 1 | W9 (06/11/2026) |
| 4.2.7 | Report 5: Integration Test Report – Cycle 2 | 2 | W9 (06/11/2026) |
| 4.2.8 | Report 3: SRS change-impact review – Cycle 2 | 1 | W9 (06/11/2026) |
| 4.2.9 | Software Package Version 2 | 1 | W9 (06/11/2026) |
| 4.2.10 | Defect correction and regression – Cycle 2 | 3 | W9 (06/11/2026) |
| 4.3 | Implementation Cycle 3 (weeks 10–11) | 36 | W11 (20/11/2026) |
| 4.3.1 | Report 4: Detailed Design Specifications (SDS) v1.3 | 2 | W10 (13/11/2026) |
| 4.3.2 | Figma design – Cycle 3 | 2 | W10 (13/11/2026) |
| 4.3.3 | Jira/CSV/Manual Import & Remaining Repository | 8 | W11 (20/11/2026) |
| 4.3.4 | Intelligent Retrieval | 6 | W11 (20/11/2026) |
| 4.3.5 | Reuse & Feedback | 3 | W11 (20/11/2026) |
| 4.3.6 | Dashboard & Audit | 3 | W11 (20/11/2026) |
| 4.3.7 | Code Package & Unit Testing Report – Cycle 3 | 4 | W11 (20/11/2026) |
| 4.3.8 | Report 5: Integration Test Cases and System Test Cases – Cycle 3 | 1 | W11 (20/11/2026) |
| 4.3.9 | Report 5: Integration Test Report – Cycle 3 | 2 | W11 (20/11/2026) |
| 4.3.10 | Report 3: SRS change-impact review – Cycle 3 | 1 | W11 (20/11/2026) |
| 4.3.11 | Software Package Version 3 | 1 | W11 (20/11/2026) |
| 4.3.12 | Defect correction and regression – Cycle 3 | 3 | W11 (20/11/2026) |
| 5 | Stage 5: Verification & Validation (weeks 12–13) | 36 | W13 (04/12/2026) |
| 5.1 | Report 5: System Test Report | 12 | W12 (27/11/2026) |
| 5.2 | Report 5: Acceptance Test Support | 8 | W13 (04/12/2026) |
| 5.3 | Report 6: User Guides (Installation Guides, User Manuals) | 10 | W12 (27/11/2026) |
| 5.4 | Final Software Package (Documents, Source Codes, etc.) | 6 | W13 (04/12/2026) |
| 6 | Stage 6: Closing (week 14) | 18 | W14 (11/12/2026) |
| 6.1 | Report 7: Final Project Report | 10 | W14 (11/12/2026) |
| 6.2 | Presentation File | 8 | W14 (11/12/2026) |
|  | Total Estimated Effort | 252 | W14 (11/12/2026) |

* 1 md = 8 person-hours.

## 4. Capacity Planning

| Item | Value |
| --- | --- |
| Hours per person per week | 36 h (4 h/day × 5 weekdays + 8 h/day × 2 weekend days) |
| Team total per week | 5 people × 36 h = 180 h/week |
| Total duration | 14 weeks |
| Gross capacity | 180 × 14 = 2,520 h |
| Buffer (meetings, coordination, unplanned — 20%) | 2,520 × 20% = 504 h |
| Effective working capacity | 2,520 × 80% = 2,016 h = 252 md (8 h/md). |

## 5. Project Objectives

| # | Metric | Unit | Planned | Actual | Notes / References |
| --- | --- | --- | --- | --- | --- |
| 1 | Effort Usage | Man-day | ≤252 |  | 2,016 effective hours; 8 h/md. |
| 2 | Review Defects | No of defects | ≤40 |  | Planning threshold; close baseline-blocking findings. |
| 3 | Unit Test Defects | No of defects | ≤30 |  | Report 5; log and fix all detected defects. |
| 4 | Integration Test Defects | No of defects | ≤20 |  | Report 5; authorization, Jira/import, review and search. |
| 5 | System Test Defects | No of defects | ≤15 |  | Report 5; no open Critical/High at exit. |
| 6 | Acceptance Test Defects | No of defects | ≤5 |  | Report 5; agreed scenarios pass, no open Critical/High. |
| 7 | Timeliness | % | ≥90 |  | On-time deliverables / committed deliverables ×100. |
| 8 | Requirement Completeness | % | 100 |  | Verified MVP requirements / baselined MVP requirements ×100; ≤75% fails. |
| 9 | Unit Test Coverage – Line | % | 100 |  | Internal target for service/domain logic; build coverage report. |
| 10 | Unit Test Coverage – Branch | % | 100 |  | Internal target for service/domain logic; JaCoCo/Vitest. |
| 11 | Static Code Quality | No of Critical issues | 0 |  | SonarQube CI before merge/release. |
| 12 | Search / Issue Panel Performance | seconds | ≤2 |  | ≤50,000 tickets; embedding service available. |
| 13 | Import Duplicate Prevention | No of duplicates | 0 |  | Reject existing CSV/manual Ticket IDs; Jira excludes existing Tickets. |

## 6. Risks and Mitigations

| # | Risk | Possible | Impact | Mitigation |
| --- | --- | --- | --- | --- |
| R01 | Jira App, embeddings and privacy masking exceed team experience. | High | High | Developers prove Jira/OIDC and Ollama/OpenRouter/pgvector integration in W2–W5; test masking and keyword fallback. Assign owner/backup; escalate blockers over 2 working days. |
| R03 | Workload/rework causes delivery delay. | Medium | High | PM limits In Progress to 3 cards and Review/Test to 2; swarm blockers and reallocate tasks. At >10% forecast overrun, use buffer or raise a schedule change; do not exceed period capacity. |
| R04 | Requirements change or SRS residual conflicts affect delivery. | High | High | BA records conflicting sources. PM assesses scope, WBS, capacity and test impacts through change control; obtain a baseline decision before affected work and update Reports 1/2/4/5/6 as applicable. |
| R05 | Absence/full-time work reduces available hours. | Medium | Medium | Confirm weekly hours; assign owner/backup and maintain handover notes. For >1 planned day lost, backup takes critical tasks and PM recalculates capacity and reallocates work. |

# II. Management Approach

## 1. Project Process/Methodology

The team uses Kanban with the states Backlog → To Do → In Progress → Review/Test → Done. In Progress has a team WIP limit of 3 cards; Review/Test has a limit of 2 cards. When Review/Test is full, members help clear the queue before starting more work. The diagram shows the normal flow and the rework loop.

Figure 1. Kanban delivery process and review/testing rework loop.

Backlog cards are prioritized by approved scope, dependency and risk. A card enters To Do only when its scope and acceptance criteria are clear, it has a WBS ID, estimate and SRS/test reference, and required inputs or predecessor work are available. Members pull work according to their skills and available capacity, observing dependencies and the WIP limit; the capstone PM helps rebalance workload.

- In Progress moves to Review/Test when implementation and relevant unit checks are complete, a reviewable change and test data are available, and the review queue has capacity. Review/Test moves to Done after independent peer review, passing CI and the planned tests, recorded evidence and traceability, updated documentation, and closure of blocking defects. Failed review or testing returns the card to In Progress with findings and an owner; it is never marked Done before the correction is verified.

- A blocked card stays visible in its current state and counts toward that state’s WIP limit. Record the blocker, owner and next action; members help resolve it, and the capstone PM escalates blockers lasting more than two working days. Daily meetings check progress, blockers and dependencies and rebalance current work. Weekly reviews inspect completed increments and test findings, refresh the Backlog and To Do priorities, and adjust workload to available capacity.

- The three two-week implementation cycles are academic delivery checkpoints within continuous Kanban. They are not Scrum sprints. At each checkpoint, the team demonstrates the planned increment, reviews test evidence and packages accepted work; unfinished cards remain visible and the capstone PM updates the dependency and capacity forecast.

## 2. Quality Management

Quality activities

| Activity | Approach | Owner | When / Frequency |
| --- | --- | --- | --- |
| Defect prevention | Agree conventions and Definition of Done; prepare tests for permissions, Ticket transitions, duplicate IDs, PII masking and failure paths. | PM, BA, Developers | Before development; continuous |
| Document review | A non-author checks template, consistency and requirement traceability. Log owner/due date; close blocking findings before baseline. | Author, peer reviewer, PM | Before each baseline |
| Code review | Independent Developer approval; check access, PII, transitions, validation and tests. CI and SonarQube must pass with 0 Critical issues. | Developers | Every pull request |
| Unit testing | JUnit 5/Mockito and Vitest/React Testing Library; test service/domain success/error paths. Internal line/branch coverage targets: 100%. | Technical contributors; Developers | During implementation; each cycle |
| Integration testing | Cycle 1: 4.1.7/4.1.8 identity, permissions, Jira/shared contracts. Cycle 2: 4.2.6/4.2.7 Ticket Detail/Evidence, submission/ resubmission and review/publication. Cycle 3: 4.3.8/4.3.9 direct imports, retrieval, Feedback, dashboards/audit and earlier-flow regression. Record cases/results in Report 5; include SMTP failure/retries. | Tester, Developers | Each cycle |
| System testing | Staging tests against SRS functionality/NFRs; one Workspace, multiple Departments/ Projects; regression for earlier modules. | Tester | Each cycle; full W12–W13 |
| Acceptance testing | Invited users perform current business-flow scenarios as Staff, Project Manager and Admin; Lecturer confirms results. | BA, Tester, PM | W12–W13 |
| Defect management | Jira records reproduction, requirement, severity, owner and due date. Triage Critical/High within one working day; retest fixes before closure. | Tester, PM | Continuous |

Quality gates: reviewed/baselined deliverables, passing CI and planned tests, updated traceability/metrics, and no open Critical/High defects. The capstone PM records stage/cycle acceptance against the planned package flows in I.3; all cycle outputs below are planning commitments, not statements of completed work.

Testing approach:

System testing uses black-box scenarios from Report 3 on staging.

• Access: Admin account/Workspace/Department management and assignment of Project Managers to Departments; Project Manager creation, configuration, removal and Staff membership for managed Projects; Department ticket visibility; member-only authoring and manager-only review/import. Verify the Active Project handover exception, blocked deactivation without a replacement, Guest sign-in and deleted-Department freezing.

• Lifecycle: Pending review → Published / Rejected / Changes requested / Expired; Changes requested → Pending review / Expired; Published ↔ Unpublished; Expired → Pending review; Rejected is terminal. Draft is not a Ticket. Test review dates, empty-Solution rejection and direct import publication.

• Imports/privacy: Jira ≤100 resolved issues, CSV UTF-8 ≤10 MB with required Solutions, manual unique Ticket IDs; Evidence ≤5 files ×10 MB. Test privacy masking and prohibited AI payloads; AI failure allows manual authoring and keyword search.

• NFRs: page/form ≤2 seconds with ≤100 active users; Search/Issue Panel ≤2 seconds at ≤50,000 tickets; CSV preview ≤60 seconds; Jira preview ≤30 and Finish ≤5; queue ≤5 seconds; expiration job ≤30 minutes. Check TLS, sessions, backups, email retries and desktop/browser usability.

• Entry: reviewed cases/data and passing integration build. Exit: all planned cases executed with evidence, no open Critical/High defects.

Acceptance testing is performed in W12–W13 on staging. Scenarios cover Version 1 setup and permissions, Version 2 Submit Solution → View Ticket/Solution/Evidence → Review → Publish (including changes and resubmission), and Version 3 Published Search/Feedback, Jira/CSV/manual direct import publication and governance. Scenarios and expected results trace to Report 3 and the WBS packages below.

• Participants: supervising Lecturer and invited users acting as Staff, Project Manager and Admin, with Guest used for signed-out sign-in scenarios. The capstone PM coordinates acceptance; this team responsibility does not grant product Project Manager permissions.

• BA prepares preconditions, steps, expected results and SRS references; Tester dry-runs scenarios and prepares one-Workspace datasets.

• Users perform the scenarios and record pass/fail and comments; the team observes.

• Failed steps become defects; fix and rerun affected scenarios.

• Acceptance closes when agreed scenarios pass, no Critical/High defects remain and the Lecturer confirms results.

## 3. Project Training Plan

| Training Area | Participants | Duration | Notes |
| --- | --- | --- | --- |
| Git / GitHub | All team | 01/10/2026 (1 day) | Branch/commit conventions, pull request review and CI. |
| JUnit 5 / Mockito; Vitest / React Testing Library | All technical contributors | 02/10–03/10/2026 | Backend and frontend tests with coverage evidence. |
| Semantic search / embedding / AI | Trần Hải Anh; Developer backup | 26/09–03/10/2026 | Ollama/OpenRouter, pgvector, PII masking and keyword fallback. |

## 4. Responsibility Assignments

RACI: R = Responsible; A = Accountable; C = Consulted; I = Informed. The capstone PM coordinates project management; product Project Manager is an application role. All members contribute to technical delivery under Developer review.

| # | Work Package | Đặng Nhật Minh (PM) | Đặng Tấn Bình (BA) | Trần Trung Hiếu (Developer) | Trần Hải Anh (Developer) | Phạm Tùng Dương (Tester) |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Stage 1: Project Initiating (week 1) |  |  |  |  |  |
| 1.1 | Report 1 (Project Introduction) | I | A/R | I | I | C |
| 2 | Stage 2: Project Planning & Initial Requirements (weeks 2–3) |  |  |  |  |  |
| 2.1 | Report 3: SRS v0.9 (Overall Requirement) | I | A/R | I | I | C |
| 2.2 | Vertical Prototypes (Code Demo) | R | R | A/R | R | R |
| 2.3 | Report 2: Project Management Plan initial baseline | A/R | C | I | I | C |
| 3 | Stage 3: Software Design (weeks 4–5) |  |  |  |  |  |
| 3.1 | Vertical Prototypes (Proof Of Concepts) | I | R | R | A/R | R |
| 3.2 | Report 4: SDS v1.0 (High Level Design Specifications) | I | C | R | A/R | C |
| 3.3 | Report 5: Test Planning | I | R | I | I | A/R |
| 3.4 | Report 3: detailed-requirements baseline review | I | A/R | I | I | C |
| 3.5 | Figma design (overall UI/UX wireframes) | I | R | A/R | I | C |
| 4 | Stage 4: Implementation (weeks 6–11) |  |  |  |  |  |
| 4.1.1 4.2.1 4.3.1 | Report 4: Detailed Design Specifications (SDS) v1.1 Report 4: Detailed Design Specifications (SDS) v1.2 Report 4: Detailed Design Specifications (SDS) v1.3 | I | R | I | A/R | C |
| 4.1.2 4.2.2 4.3.2 | Figma design – Cycle 1 Figma design – Cycle 2 Figma design – Cycle 3 | I | R | A/R | I | C |
| 4.1.3 | Role-Based Access Control | R | R | R | A/R | C |
| 4.1.4 | Workspace & Department Management | R | R | A/R | R | C |
| 4.1.5 | Jira Integration and Shared Data/API Foundation | R | R | R | A/R | C |
| 4.1.6 4.2.5 4.3.7 | Code Package & Unit Testing Report – Cycle 1 Code Package & Unit Testing Report – Cycle 2 Code Package & Unit Testing Report – Cycle 3 | I | C | R | A/R | R |
| 4.1.7 | Report 5: Integration Test Cases – Cycle 1 | I | R | I | I | A/R |
| 4.1.8 4.2.7 4.3.9 | Report 5: Integration Test Report – Cycle 1 Report 5: Integration Test Report – Cycle 2 Report 5: Integration Test Report – Cycle 3 | R | C | I | I | A/R |
| 4.1.9 4.2.8 4.3.10 | Report 3: SRS change-impact review – Cycle 1 Report 3: SRS change-impact review – Cycle 2 Report 3: SRS change-impact review – Cycle 3 | R | A/R | I | I | C |
| 4.1.10 | Software Package Version 1 | A/R | C | R | R | C |
| 4.1.11 | Defect correction and regression – Cycle 1 | I | C | R | A/R | R |
| 4.2.11 | Ticket/Solution/Evidence Foundation & Ticket Detail | I | C | R | A/R | R |
| 4.2.3 | Solution Authoring & Standardisation | I | R | A/R | R | R |
| 4.2.4 | Review & Approval Workflow | I | R | R | A/R | R |
| 4.2.6 | Report 5: Integration Test Cases – Cycle 2 | I | R | I | I | A/R |
| 4.2.9 | Software Package Version 2 | A/R | C | R | R | C |
| 4.2.10 | Defect correction and regression – Cycle 2 | I | C | R | A/R | R |
| 4.3.3 | Jira/CSV/Manual Import & Remaining Repository | I | R | R | A/R | R |
| 4.3.4 | Intelligent Retrieval | I | R | A/R | R | R |
| 4.3.5 | Reuse & Feedback | I | R | A/R | R | R |
| 4.3.6 | Dashboard & Audit | I | R | R | A/R | R |
| 4.3.8 | Report 5: Integration Test Cases and System Test Cases – Cycle 3 | I | R | I | I | A/R |
| 4.3.11 | Software Package Version 3 | A/R | C | R | R | C |
| 4.3.12 | Defect correction and regression – Cycle 3 | I | C | R | A/R | R |
| 5 | Stage 5: Verification & Validation (weeks 12–13) |  |  |  |  |  |
| 5.1 | Report 5: System Test Report | I | C | R | R | A/R |
| 5.2 | Report 5: Acceptance Test Support | R | R | I | I | A/R |
| 5.3 | Report 6: User Guides (Installation Guides, User Manuals) | I | A/R | R | R | C |
| 5.4 | Final Software Package (Documents, Source Codes, etc.) | A/R | C | R | R | R |
| 6 | Stage 6: Closing (week 14) |  |  |  |  |  |
| 6.1 | Report 7: Final Project Report | A/R | R | I | I | R |
| 6.2 | Presentation File | A/R | R | I | I | C |

## 5. Project Communications

| Communication Item | Who/ Target | Purpose | When, Frequency | Type, Tool, Method(s) |
| --- | --- | --- | --- | --- |
| Daily team meeting | All team | Completed work, next tasks and blockers. | Daily, 21:00 UTC+7 | Discord |
| Weekly review/planning | All team | Review deliverables, priorities, capacity and risks. | Saturday, 09:00–15:00 UTC+7 | At school; tracking/minutes |
| Weekly supervisor/lecturer report | All team and Lecturer | Report progress, issues and required decisions. | Sunday, 13:00 UTC+7 | Google Meet; weekly report |

## 6. Configuration Management

### 6.1 Document Management

Reports, meeting minutes, weekly reports, tracking and presentation files are stored in the shared Google Drive Document folder.

Use one folder per Report 1–7 plus Meeting Minutes, Weekly Reports, Project Tracking and Presentation. Each report has Working and read-only Baselines areas. Team members edit Working files; Lecturer comments; PM manages access.

Name baseline files <Report code>_<Document name>_v<major>.<minor>. Keep one live working file.

• v0.x: draft; v1.0: first baseline; v1.x: reviewed minor update; v2.0+: major revision.

Change Log records date, A/M/D, owner and description. Google Drive history supports recovery; approved baseline copies are retained.

Document workflow: author drafts → non-author reviews → author fixes → PM baselines. Prior baselines remain read-only.

Change control: BA records a requirement change/conflict; PM assesses scope, schedule, effort, WBS/RACI, risks and tests. When Report 3 changes, assess and update affected Reports 1, 2, 4, 5, 6 and related code/UI/test/guide artifacts. Obtain the SRS decision, review affected updates and re-baseline them together.

Document owners and baselines follow the WBS below.

| Document | Owner (role) | Planned baselines |
| --- | --- | --- |
| Report 1 – Project Introduction | BA | Stage 1 baseline |
| Report 2 – Project Management Plan | PM | Stage 2 baseline; v2.1 revision 05/10/2026; scope/process/WBS alignment revision 08/10/2026 |
| Report 3 – Software Requirement Specification | BA | Current baseline; reviewed change updates at checkpoints |
| Report 4 – Software Design Specification | Developers | Stage 3; Cycle 1–3 updates |
| Report 5 – Test Documentation and reports | Tester | Stage 3 plan; cycle cases/reports; Stage 5 final reports |
| Report 6 – User Guides | BA | Stage 5 baseline |
| Report 7 – Final Project Report and presentation | PM | Stage 6 baseline |
| Meeting minutes, Weekly Reports, Project Tracking | PM | Updated weekly |

Export baselines to PDF; PM retains an offline copy at each stage. Keep project records through final grading.

### 6.2 Source Code Management

Source code uses Git in a private GitHub mono-repo. Documents remain on Google Drive. Jira tracks tasks/defects and links pull requests through GitHub for Atlassian.

Repository structure:

| Folder | Content | Owner |
| --- | --- | --- |
| backend/ | Java/Spring Boot application organized as a modular monolith (one package per module: identity, intake, solution, …) | All members – Reviewer: Tran Hai Anh |
| frontend/ | React single-page application (shared layout shell and feature pages) | All members – Reviewer: Tran Trung Hieu |
| infra/ | Docker Compose files for each environment, reverse-proxy (Caddy) configuration and server setup scripts | All members – Reviewer: Tran Trung Hieu |
| .github/ | CI/CD workflows, CODEOWNERS file, pull request template | Tran Trung Hieu |

Trunk-Based Development: main is the only long-lived branch. Create short-lived branches from main, submit reviewed pull requests, squash merge and delete the branch. Passing merges deploy to staging.

Branch names use <type>/<module>-<description>. Branch types are listed below.

| Branch type | Purpose | Example |
| --- | --- | --- |
| feature/ | New functionality | feature/solution-draft-endpoint |
| fix/ | Bug found during development or testing | fix/search-empty-query |
| hotfix/ | Urgent fix for a production issue | hotfix/identity-login-error |
| chore/ | Build, dependency or configuration change | chore/ci-upgrade-spring-boot |
| test/ | Adding or updating tests only | test/intake-duplicate-import |

Commit messages follow Conventional Commits, checked by commitlint.

Development workflow: create branch/card → implement with tests → synchronize main → independent review and passing CI → squash merge → staging validation.

CI runs build/tests, coverage, Spotless/Checkstyle, Prettier/ESLint, commitlint, secret scanning and SonarQube. Require 0 Critical issues before merge.

Protect main: no direct/force pushes or deletion; required passing CI, current branch and independent CODEOWNERS approval; squash merges for linear history.

• Use Semantic Versioning, annotated release tags and GitHub Releases. A tested image tagged by commit SHA/version is promoted after release approval; rollback redeploys the previous image.

• Spring Data JPA/Hibernate handles data access. Version schema changes in immutable Flyway migrations.

• Exclude secrets/.env from Git; commit only .env.example placeholders.

### 6.3 Tools & Infrastructures

| Category | Tools / Infrastructure |
| --- | --- |
| Technology | Java 21 / Spring Boot 4; React / Ant Design ProComponents; external T-Solve Jira App |
| Database | PostgreSQL / pgvector; Spring Data JPA / Hibernate; Flyway |
| IDEs/Editors | IntelliJ IDEA; Visual Studio Code |
| AI Coding Assistants | Claude Code; Codex |
| Diagramming | Visual Paradigm; Figma |
| Documentation | Google Docs/Sheets/Slides; Swagger UI / springdoc-openapi |
| Version Control | Git / GitHub (source); Google Drive (documents) |
| CI/CD | GitHub Actions; GitHub Container Registry |
| Code Quality | SonarQube Cloud; Spotless/Checkstyle; Prettier/ESLint; commitlint; gitleaks; Dependabot |
| Testing | JUnit 5 / Mockito / JaCoCo; Vitest / React Testing Library; Postman |
| Database Client | DBeaver |
| Deployment Server | Vietnam-region VPS; Docker / Docker Compose; Caddy HTTPS; Google OIDC; SMTP; Ollama; OpenRouter |
| Monitoring | Grafana Alloy; Prometheus; Loki; Grafana team alerts; UptimeRobot |
| Project Management | Jira tasks/defects; Google Sheets schedule/weekly reports |
| Communication | Discord; Google Meet |